## Gantt Chart Template
TASK NUMBER | WBS NUMBER | TASK TITLE | TASK PARTICIPANTS | START DATE | DUE DATE | DURATION | PREDECESSORS | WEEK 1 (Oct 21 - Oct 27) | [6 empty] | WEEK 2 (Oct 28 - Nov 3) | [6 empty] | WEEK 3 (Nov 4 - Nov 10) | [6 empty] | WEEK 4 (Nov 11 - Nov 17) | [6 empty] | WEEK 5 (Nov 18 - Nov 24) | [6 empty] | WEEK 6 (Nov 25 - Dec 1) | [6 empty] | WEEK 7 (Dec 2 - Dec 8) | [6 empty] | WEEK 8 (Dec 9 - Dec 15) | [6 empty] | WEEK 9 (Dec 16 - Dec 22) | [6 empty] | WEEK 10 (Dec 23 - Dec 29) | [6 empty] | WEEK 11 (Dec 30 - Jan 5) | [6 empty] | WEEK 12 (Jan 6 - Jan 12) | [6 empty] | WEEK 13 (Jan 13 - Jan 19) | [6 empty] | WEEK 14 (Jan 20 - Jan 26) | [6 empty] | WEEK 15 (Jan 27 - Feb 2) | [6 empty] | WEEK 16 (Feb 3 - Feb 9) | [6 empty] | WEEK 17 (Feb 10 - Feb 16) | [6 empty] | WEEK 18 (Feb 17 - Feb 23) | [6 empty] | WEEK 19 (Feb 24 - Mar 2) | [6 empty] | WEEK 20 (Mar 3 - Mar 9) | [6 empty] | WEEK 21 (Mar 10 - Mar 16)
[8 empty] | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W | TH | F | S | SU | M | T | W
1 | 1 | Milestone #1: 1st Peer Testing |  |  |  | 49 days | bar: WEEK 1 (Oct 21 - Oct 27) TH to WEEK 7 (Dec 2 - Dec 8) W
2 | 1.1 | Design Main Menu Layout |  | 2021-10-21 | 2021-11-11 | 21 days | - | bar: WEEK 1 (Oct 21 - Oct 27) TH to WEEK 3 (Nov 4 - Nov 10) W
3 | 1.2 | Design Ethical Issue Layout |  | 2021-10-21 | 2021-11-11 | 21 days | - | bar: WEEK 1 (Oct 21 - Oct 27) TH to WEEK 3 (Nov 4 - Nov 10) W
4 | 1.3 | Implement Database |  | 2021-10-28 | 2021-11-18 | 21 days | - | bar: WEEK 2 (Oct 28 - Nov 3) TH to WEEK 4 (Nov 11 - Nov 17) W
5 | 1.4 | Testing/Debugging |  | 2021-11-11 | 2021-11-18 | 7 days | 2;3
6 | 1.5 | Prepare Prototype |  | 2021-11-18 | 2021-11-25 | 7 days | 4;5 | bar: WEEK 5 (Nov 18 - Nov 24) TH to WEEK 5 (Nov 18 - Nov 24) W
7 | 1.6 | Peer Testing |  | 2021-11-25 | 2021-12-02 | 7 days | 6
8 | 1.7 | Feedback |  | 2021-12-02 | 2021-12-09 | 7 days | 7 | bar: WEEK 7 (Dec 2 - Dec 8) TH to WEEK 7 (Dec 2 - Dec 8) W
9 | 2 | Mileston #2: 2nd Peer Testing |  |  |  | 84 days | bar: WEEK 8 (Dec 9 - Dec 15) TH to WEEK 9 (Dec 16 - Dec 22) W; WEEK 12 (Jan 6 - Jan 12) TH to WEEK 21 (Mar 10 - Mar 16) W
10 | 2.1 | Design Stakeholder Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8 | bar: WEEK 3 (Nov 4 - Nov 10) TH to WEEK 3 (Nov 4 - Nov 10) W
11 | 2.2 | Implement Stakeholder Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8
11 | 2.2 | Design Utilitarianism Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8 | bar: WEEK 3 (Nov 4 - Nov 10) TH to WEEK 3 (Nov 4 - Nov 10) W
12 | 2.3 | Implement Utilitarianism Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8
12 | 2.3 | Design Deontology Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8 | bar: WEEK 12 (Jan 6 - Jan 12) TH to WEEK 13 (Jan 13 - Jan 19) W
13 | 2.4 | Implement Virtue Ethics Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8 | bar: WEEK 13 (Jan 13 - Jan 19) TH to WEEK 13 (Jan 13 - Jan 19) W
13 | 2.4 | Design Virtue Ethics Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8 | WEEK 10 (Dec 23 - Dec 29) SU: Winter Break
14 | 2.5 | Implement Virtue Ethics Layout |  | 2022-01-06 | 2022-02-24 | 49 days | 8 | bar: WEEK 10 (Dec 23 - Dec 29) SU; WEEK 14 (Jan 20 - Jan 26) TH to WEEK 15 (Jan 27 - Feb 2) W
13 | 2.4 | Design Care Ethics Layout |  | 2021-12-09 | 2022-02-10 | 49 days | 8 | bar: WEEK 10 (Dec 23 - Dec 29) SU; WEEK 13 (Jan 13 - Jan 19) TH to WEEK 15 (Jan 27 - Feb 2) W
14 | 2.5 | Implement Care Ethics Layout |  | 2022-01-06 | 2022-02-24 | 49 days | 8 | bar: WEEK 10 (Dec 23 - Dec 29) SU; WEEK 14 (Jan 20 - Jan 26) TH to WEEK 15 (Jan 27 - Feb 2) W
14 | 2.5 | Implement Student Account |  | 2022-01-06 | 2022-02-24 | 49 days | 8 | bar: WEEK 3 (Nov 4 - Nov 10) TH to WEEK 4 (Nov 11 - Nov 17) W; WEEK 14 (Jan 20 - Jan 26) TH to WEEK 18 (Feb 17 - Feb 23) W
15 | 2.6 | Implement Class Creation |  | 2022-01-06 | 2022-02-24 | 49 days | 8 | bar: WEEK 16 (Feb 3 - Feb 9) TH to WEEK 18 (Feb 17 - Feb 23) W
16 | 2.7 | Testing/Debugging |  | 2022-02-10 | 2022-02-24 | 14 days | 10;11;12;13 | bar: WEEK 17 (Feb 10 - Feb 16) TH to WEEK 18 (Feb 17 - Feb 23) W
17 | 2.8 | Prepare Prototype |  | 2022-02-24 | 2022-03-03 | 7 days | 14;15;16 | bar: WEEK 19 (Feb 24 - Mar 2) TH to WEEK 19 (Feb 24 - Mar 2) W
18 | 2.9 | Peer Testing |  | 2022-03-03 | 2022-03-10 | 7 days | 17
19 | 3 | Feedback |  | 2022-03-10 | 2022-03-17 | 7 days | 18 | bar: WEEK 21 (Mar 10 - Mar 16) TH to WEEK 21 (Mar 10 - Mar 16) W
16 | 3
17 | 3.1
18 | 3.2
19 | 3.2.1
20 | 3.2.2
21 | 3.2.3
22 | 3.3
23 | 3.4